## 表格_20260312 (1)
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA-001 | TA Create Personal Application Profile | As a TA Applicant, I want to create a personal application profile with basic info, professional skills and course experience, So that I can complete registration and apply for TA positions officially | Must Have | 1 | 1. Provide fixed input fields: Name / Student ID / Email / Courses Available to Teach / Skill Tags / Contact Number 2. Non-null validation for Student ID and Email; Email format validation (must contain @), with clear error prompts on failure 3. Generate a unique TA ID after profile creation, bound to the information and saved to a JSON file 4. Support editing and saving of profile information; synchronize updates to local storage after modification 5. Password is required and encrypted during storage | 8 | Skill tags are pre-set multiple-choice (e.g., Java/English/Teaching) to align with the recruitment requirements of the International School of BUPT | 2026-03-07 | 2026-03-15
TA-002 | TA Upload Personal Resume and Link to Profile | As a TA Applicant, I want to upload my CV file and bind it to my personal profile, So that Module Organisers can view my detailed background for application review | Must Have | 1 | 1. Support uploading CV files in txt/pdf/doc format with a file size limit of ≤10MB; prompt an error if exceeded 2. Record the local file path after successful upload, bind it to the TA ID and save to JSON 3. Support re-uploading CV (overwrite the original path) and deleting (clear the path record) 4. The profile page can view the CV upload status and file path; click the path to open the file | 5 | Only store the file path, do not parse CV content; the delete operation only modifies the path and does not delete local files | 2026-03-10 | 2026-03-16
TA-003 | TA Query List of Active Applicable Positions | As a TA Applicant, I want to view a list of all active TA jobs with core information, So that I can select suitable positions matching my skills and experience | Must Have | 2 | 1. Only display positions with the status of「Recruiting」in the list; off-market positions are automatically hidden 2. Sort the list in reverse chronological order of release time, showing Position ID / Course Name / Position Type / Weekly Workload / MO Name 3. Click on a position entry to view full details (including skill requirements / job content / application deadline) 4. Support page refresh to synchronize the latest position data from the local CSV | 5 | Implement basic pagination (10 items per page), no advanced filtering | 2026-03-20 | 2026-03-28
TA-004 | TA Submit Position Application | As a TA Applicant, I want to submit an application for a selected active TA job, So that Module Organisers can receive and review my application | Must Have | 2 | 1. Click the「Apply」button on the position detail page to automatically associate the current TA ID and Position ID 2. A TA ID can only submit 1 application for the same Position ID; prompt「Already Applied」for repeated applications 3. Generate a unique application ID after submission, with the default status of「Pending」, saved to CSV 4. Application records include: TA ID / Position ID / Application ID / Application Time / Application Status | 8 | A TA can apply for multiple different positions; applications cannot be withdrawn after submission, only the status can be viewed | 2026-03-22 | 2026-03-30
TA-005 | TA Query Personal Application Records and Status | As a TA Applicant, I want to view all my submitted TA applications and their real-time status, So that I can know the review result from Module Organisers in time | Must Have | 2 | 1. Display all personal application records in reverse chronological order of application time, including Course Name / Application Time / Application Status 2. Application status includes「Pending/Approved/Rejected」, synchronized with MO's review operations in real time 3. Click on an application record to view details, including MO review comments (if any, max 50 characters) 4. Support page refresh to synchronize the latest status data from the local CSV | 3 | Status changes are triggered by MO operations; TA can only view and has no modification rights; review comments are optional for MO | 2026-03-25 | 2026-04-01
TA-006 | TA Edit Personal Application Profile | As a TA Applicant, I want to edit and save the information in my personal profile, So that I can update my latest skills and course experience for new applications | Should Have | 3 | 1. An「Edit」button is provided on the profile page; all fields (except TA ID) are editable after clicking 2. Re-validate Student ID and Email format after editing; save is not allowed if validation fails 3. Overwrite the original data with new information after saving, and synchronize updates to the local JSON file | 3 | TA ID is a unique identifier and cannot be edited; modifications do not affect submitted application records | 2026-04-06 | 2026-04-12
TA-007 | AI Identify Skill Gaps for TA Job Applications | As a TA Applicant, I want the system to compare my skills with the selected job's requirements and identify missing skills, So that I can know my skill gaps and improve my application qualifications | Could Have | 4 | 1. A「Skill Gap Analysis」button is provided on the position detail page, clickable only by the current TA 2. After clicking, the system extracts the position's skill requirements and the TA's skills, listing the missing skills 3. The analysis result is visible only to the user, with no access rights for other users 4. Support exporting the list of skill gaps as a TXT file and saving it locally | 8 | Reuse the core keyword matching logic from MO-010; only display missing skills, no learning resource recommendations | 2026-04-22 | 2026-04-30
TA-008 | TA Filter Applicable Positions (by Skill/Type) | As a TA Applicant, I want to filter active TA jobs by skill requirements or job type, So that I can quickly find positions matching my ability | Could Have | 4 | 1. A filter bar is provided on the position list page: Skill Tags (multiple choice), Position Type (single choice: Module/Invigilation) 2. Support superposition of multiple conditions for filtering; click「Reset」to clear all filter conditions 3. Refresh the list in real time after filtering; prompt「No Matched Jobs」if no qualified positions are found 4. Filter results only take effect for the current TA and do not affect other users | 5 | Only implement precise matching filtering; filter conditions are preset fields when the position is published | 2026-04-20 | 2026-04-28
MO-001 | MO Post TA Recruitment Position | As a Module Organiser, I want to post a TA job with detailed information including requirements and workload, So that TA Applicants can view and apply for the position I need | Must Have | 1 | 1. Provide fixed input fields: Course Name / Position Type / Skill Requirements / Weekly Workload / Application Deadline / MO Name / MO Email 2. Non-null validation for Course Name, Position Type and Weekly Workload; numeric validation for workload, save is not allowed if validation fails 3. Generate a unique Position ID after successful release, with the default status of「Recruiting」, saved to CSV 4. Support viewing the position information immediately after release and including it in the active position list | 8 | Position type can only be selected as「Module TA」/「Invigilation TA」; workload unit is hours/week | 2026-03-07 | 2026-03-17
MO-002 | MO View All Posted Positions | As a Module Organiser, I want to view all TA jobs I have posted with their status, So that I can manage my published positions uniformly | Must Have | 2 | 1. Display all positions posted by the user in reverse chronological order of release time, including Position ID / Course Name / Position Type / Position Status 2. Position status includes「Recruiting/Closed」 3. Click on a position entry to view full information and the number of application records for the position 4. Support page refresh to synchronize the latest position data from the local CSV | 3 | Can only view positions posted by oneself, with no access rights to positions of other MOs | 2026-03-23 | 2026-03-29
MO-003 | MO Edit Posted Active Positions | As a Module Organiser, I want to edit the information of my posted active TA jobs, So that I can update the latest job requirements and workload | Must Have | 2 | 1. Only positions with the status of「Recruiting」are editable;「Closed」positions are not editable 2. After clicking the「Edit」button, all fields (except Position ID) are modifiable, with the same validation rules as when publishing 3. Synchronize updates to the local CSV after modification; submitted application records can view the latest position information | 5 | Position ID is a unique identifier and cannot be edited; modifications do not affect submitted application records | 2026-03-25 | 2026-03-31
MO-004 | MO Close Posted Positions | As a Module Organiser, I want to set my posted TA job status to Closed, So that I can stop receiving new applications when the position is filled | Must Have | 2 | 1. A「Close Job」button is provided for positions with the status of「Recruiting」, with a secondary confirmation after clicking 2. After confirmation, the position status is changed to「Closed」, synchronized to the local CSV, and removed from the active list 3. Once closed, the status cannot be restored to「Recruiting」; only position information and historical application records can be viewed 4. The close operation does not delete position data, retaining historical records for subsequent viewing | 3 | Can only close positions posted by oneself; closed positions still allow review of submitted application records | 2026-03-27 | 2026-04-02
MO-005 | MO View Application Records for Posted Positions | As a Module Organiser, I want to view all applications for my posted TA jobs, So that I can review the candidates for my positions | Must Have | 3 | 1. Enter the position detail page to view all application records for the position, sorted in reverse chronological order of application time 2. Application records display: TA Name / TA ID / Application Time / Application Status / Profile Access Entry 3. Click「View Profile」to open the applicant's personal profile (including basic information / skills / CV path) 4. Support filtering by application status (Pending/Approved/Rejected) | 5 | Can only view application records for positions posted by oneself; can view the applicant's full profile but has no modification rights | 2026-04-03 | 2026-04-10
MO-006 | MO Review TA Job Applications (Approve/Reject) | As a Module Organiser, I want to review TA applications and mark them as Approved or Rejected, So that I can select suitable TAs for my posted positions | Must Have | 3 | 1. Only applications with the status of「Pending」are reviewable; reviewed applications cannot be operated repeatedly 2. Provide「Approve」and「Reject」buttons; review comments can be filled in after clicking (optional, ≤50 characters) 3. After review, the application status is synchronized to the CSV, and the TA can view the status and comments in real time 4. The review operation is traceable, recording MO ID / Review Time / Review Result, saved locally | 8 | Review results cannot be modified once submitted; comments are optional, and the TA only displays the status if there are no comments | 2026-04-05 | 2026-04-12
MO-007 | MO Filter Applicants by Skill/Experience | As a Module Organiser, I want to filter TA applicants for my job by their skills or course experience, So that I can quickly find qualified candidates | Should Have | 3 | 1. A filter bar is provided on the position application list page: Skill Tags (multiple choice), Courses Taught (multiple choice) 2. Support superposition of multiple conditions for filtering; click「Reset」to clear all filter conditions 3. Refresh the list in real time after filtering; prompt「No Qualified Applicants」if no qualified applicants are found 4. Filter results only take effect for the current MO and do not affect other users | 5 | Only implement precise matching filtering; filter conditions are preset fields in the TA's profile | 2026-04-08 | 2026-04-15
MO-008 | MO Batch Review TA Job Applications | As a Module Organiser, I want to approve or reject multiple TA applications at one time, So that I can improve the efficiency of application review | Should Have | 4 | 1. Support checking multiple application records with the status of「Pending」on the application list page 2. Provide「Bulk Approve」and「Bulk Reject」buttons; unified comments can be filled in for batch operations 3. After batch operation, the status of all checked applications is synchronized, and the batch operation information is recorded for traceability 4. Support undoing batch operations (within 5 minutes after operation), restoring to the「Pending」status | 8 | Can only batch review application records for the same position; batch comments take effect for all checked applications | 2026-04-24 | 2026-05-01
MO-009 | MO View Workload of Hired TAs | As a Module Organiser, I want to view the workload of TAs I have approved for my jobs, So that I can know the workload distribution of my hired TAs | Could Have | 4 | 1. Provide a「My Hired TAs」page displaying all TA information hired by the user 2. Information includes: TA Name / TA ID / Position Name / Weekly Workload / Hiring Time 3. Support sorting by weekly workload and viewing the total workload of a single TA (if hired for multiple positions) 4. Support exporting the list of hired TAs as a CSV file and saving it locally | 5 | Can only view the workload of TAs hired by oneself; data is derived from the weekly workload field when the position is published | 2026-04-26 | 2026-05-03
MO-010 | AI Match Positions with Applicants' Skills and Rank | As a Module Organiser, I want the system to automatically match TA applicants to my job by skill requirements and sort by matching degree, So that I can quickly find the most qualified candidates | Could Have | 4 | 1. An「AI Skill Match」button is provided on the position application list page, clickable only by the current MO 2. After clicking, the system extracts the position's skill requirements and the applicants' skills, calculating the matching degree (0-100%) 3. The application list is rearranged in descending order of matching degree, with each applicant displaying the matching degree and matching reasons 4. Support turning off AI sorting and restoring the original application list (sorted by application time) | 13 | Matching degree = (Number of overlapping skills / Total number of position skills) × 100%; matching reasons clearly mark overlapping skills | 2026-04-20 | 2026-04-28
AD-001 | AD View Overall Workload of All Hired TAs | As an Administrator, I want to view the overall workload of all TAs approved by all MOs, So that I can monitor the global TA workload distribution of the school | Must Have | 3 | 1. Provide a「TA Workload Overview」page displaying all TA information with the status of「Approved」 2. Information includes: TA Name / TA ID / Hiring MO / Position Name / Weekly Workload / Total Workload (for multiple positions) 3. Support filtering by TA Name / Course Name / MO Name, and sorting by total workload in descending order 4. Data is synchronized to the local CSV in real time, supporting page refresh to obtain the latest data | 8 | Can only view the workload of hired (Approved) TAs, with no access rights to Pending/Rejected applications; total workload is the sum of workload for all positions of a single TA | 2026-04-05 | 2026-04-12
AD-002 | AD Export TA Workload Statistics | As an Administrator, I want to export the overall TA workload data to a CSV file, So that I can analyze and archive the workload data offline | Must Have | 3 | 1. An「Export CSV」button is provided on the workload overview page; click to export all currently displayed data 2. The exported file contains complete fields: TA ID / Name / Hiring MO / Position Name / Weekly Workload / Total Workload / Hiring Time | 3 | The exported format is standard CSV, which can be opened directly with Excel; no file size limit, adapting to all hired TA data | 2026-04-07 | 2026-04-14
AD-003 | AD Count TA Workload by Course/Department | As an Administrator, I want to count the TA workload by course name or school department, So that I can know the workload distribution by different courses/departments | Should Have | 4 | 1. A「Statistics」module is provided on the workload overview page, supporting statistics by「Course Name」or「Department」 2. Statistics by course: display the total number of TAs, total workload, and average workload for each course 3. Statistics by department: display the total number of TAs, total workload, and average workload for each department 4. Display statistical results in a simple table, supporting export as a CSV file | 5 | The department field is optional when publishing a position; statistical data is calculated in real time based on the workload of hired TAs | 2026-04-24 | 2026-05-01
AD-004 | AI Mark Overloaded TAs and Provide Balancing Suggestions | As an Administrator, I want the system to mark TAs with overloaded workload and give simple adjustment suggestions, So that I can avoid individual TAs being assigned too many jobs | Want to Have | 4 | 1. AD can customize the TA weekly workload threshold (default 10 hours/week), supporting modification and saving 2. The system automatically judges the TA's total workload; TAs exceeding the threshold are highlighted in red font 3. Display「Current Workload - Threshold = Excess Amount」at the mark, and give a text suggestion of「Reduce Workload」 4. Support sorting the TA list by overload degree, prioritizing TAs with the most excess amount | 10 | Only basic threshold judgment, no automatic workload allocation function; suggestions are for reference only, requiring AD to manually coordinate MO adjustments | 2026-04-25 | 2026-05-02